## Sheet1
Project Blueprint - simplified - | [22 empty] | Observations
Status |  |  | Project Activities | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Started (Yes/No) | In Progress (%) | Complete (Yes/No) |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Yes |  | Yes | Reading | [19 empty] | Thorough reading of the project description and objectives | bar: Week 1 T 9 to Week 1 W 10; Week 1 S 13
Yes |  | Yes | Analysis | [19 empty] | Analysis of the problem (data source in the context of the project description, deliverables | bar: Week 1 T 11; Week 1 S 13
Yes |  | Yes | Comprehension | [19 empty] | Understanding of the project: Identification of entities, attributes, relationships and keys | bar: Week 1 T 11; Week 1 S 13
Yes |  | Yes | Architecture | [19 empty] | ERD and Data Flow Diagram - conceptual level | bar: Week 1 F 12 to Week 1 S 13
Yes |  | Yes | Modeling & Design | [19 empty] | ERD and Data Flow Diagram - logical level | bar: Week 1 S 13 to Week 1 S 14
Yes |  | Yes | Tools and Techniques: selection | [19 empty] | MySQL or Excel Selection to move to the execution phase | bar: Week 1 S 13 to Week 1 S 14
Yes |  | Yes | Documentation Submission for approval | [19 empty] | Documentation must include the design of the Executive Report (format and columns) | bar: Week 1 S 13; Week 2 M 15 to Week 2 S 21
No |  | No | Execution: Development and Reporting | [19 empty] | Installation of the software. Creation of database, tables, queries, report | bar: Week 1 S 13; Week 2 M 15 to Week 3 M 22
No |  | No | Executive Report and Doc Prep for final submission | [19 empty] | Prep copies of databases and/or spreadsheets used, plus supporting documentation | bar: Week 1 S 13; Week 3 M 22 to Week 3 W 24
No |  | No | Project Delivery - Due Date | [19 empty] | Submission | bar: Week 1 S 13; Week 3 T 25 to Week 3 F 26
Note: Data Governance principles must be embedded within the development framework
Note on K10: Milestone
Note on M11: Milestone
Note on U13: Due Date

## Sheet2
No | 0 | No
Yes | 10 | Yes
20
30
40
50
60
70
80
90